## Risicolog
Risks | Chance [1 t/m 5] | Impact [1 t/m 5] | Risk value | Solution | Measure | Chance [1 t/m 5]2 | Impact (after) [1 t/m 5] | Risk value (after) | Solution applied?
User loses the tag inside | 3 | 5 | 15 | Tag makes sound | Program the tag to make sound in lost mode | 1 | 4 | 4 | No | Risk value = chance x impact
User breaks button | 2 | 5 | 10 | No direct solution | Have a back-up button | 2 | 5 | 10 | No
User breaks tag | 1 | 5 | 5 | No direct solution | Have a back-up tag | 1 | 5 | 5 | No
Tag loses connection with the tablet | 2 | 5 | 10 | Connection loss warning | Add a warning for loss of connection to the app and show contacts of the caregiver | 2 | 5 | 10 | No
Button loses connection with the tablet | 2 | 3 | 6 | Connection loss warning | Add a warning for loss of connection to the app and show contacts of the caregiver | 2 | 5 | 10 | No
User breaks the tablet | 2 | 5 | 10 | No direct solution | Buy a case/screen protector for the tablet, have a back-up tablet | 2 | 5 | 10 | No
Caregiver loses access to the Buddy app | 1 | 5 | 5 | Contact support | Show contact details on the main page, maintained by | 1 | 3 | 3 | No
Buddy bot loses connection to Firebase | 1 | 5 | 5 | Connection loss warning | Add a warning for loss of connection to the app and show contacts of the caregiver | 1 | 3 | 3 | No
Buddy app loses connection to Firebase | 1 | 5 | 5 | Connection loss warning | Add a warning for loss of connection to the app and show contacts for troubleshooting | 1 | 2 | 2 | No
User repetitively clicks the button | 5 | 3 | 15 | Add click delay | Add a click delay of []s, | 2 | 2 | 4 | No
Battery of the tag runs low | 1 | 3 | 3 | Low battery warning at []% | Add a low battery warning to the app that warns the user of the inpending doom of the tag | 1 | 2 | 2 | No
Data of the button's response is not recorded correctly | 3 | 5 | 15 | Debug code | Investigate the connection between the tablet and Firestore and the data that being sent to said database. Apply fixes where's needed. | 2 | 3 | 6 | No
Button does something unsuspected | 2 | 2 | 4 | Debug code | Monitor the button's behaviour and notes down its actions. Debug the code using the new information. | 1 | 1 | 1 | No
Buddy bot doesn't response accordingly to user's actions | 2 | 3 | 6 | Debug code | Monitor the bot's behaviour and notes down its actions. Debug the code using the new information. | 1 | 2 | 2 | No
Distance from tag to the tablet is incorrectly calculated by more than []cm | 3 | 4 | 12 | Rewrite the calculation | Find the source of faulty calculation, and fix it. | 1 | 2 | 2 | No
Distance is incorrectly recorded to the database | 2 | 5 | 10 | Debug code | Investigate the connection between the tablet and Firestore and the data that being sent to said database. Apply fixes where's needed. | 1 | 3 | 3 | No
Connection between the tag and tablet is unstable | 3 | 5 | 15 | Change tag or fix code | Investigate the tag and the code. Isolate the problem and fix it if it's the code and order a new tag if it's the problem. | 1 | 3 | 3 | No
Connection between the button and tablet is unstable | 2 | 5 | 10 | Change button or fix code | Investigate the button and the code. Isolate the problem and fix it if it's the code and order a new button if it's the problem. | 1 | 3 | 3 | No

## Changelog
Version | Datum | Log
1.0 | 2024-03-01 | Document is made